## ActiveTaskList
S.No | Feature | Status | Priority | Application Concerned | Final Release Date | UI(hours) |  | API(hours) | QA(hours)
1 | Extending Admin role to spire users | Feb Release | High | Customer Portal | 26.02.2023 | 8 |  | 8 | 8
2 | Reporting | Feb Release | High | Customer Portal | 26.02.2023 | 40 | Low | 24 | 8
3 | Adding Copyright | Mid Feb Release | Medium | Customer Portal | 03.02.2023 | 8 | Medium | 0 | 2
4 | "No Record Found" Feature | Mid Feb Release | Low | Customer Portal | 03.02.2023 | 4 | High | 0 | 3
5 | Job Deletion Feature | Feb Release | Low | Crewlink & Customer Portal | 26.02.2023 | 4 |  | 16 | 8
6 | Labor Comments section - Not appearing | Mid Feb Release | Low | Customer Portal | 03.02.2023 | 4 |  | 4 | 3
7 | Mears Admin to be able to see the Approval and Reports screen in “View Only” mode to ease the bug fixing process if any | Yet to Decide | Low | Customer Portal | 26.02.2023 | 16 |  | 8 | 8
8 | Having DFR Approval Status view in Reviewer screen | Yet to Decide | High | Crewlink | 26.02.2023 | 8 |  | 8 | 8
9 | Filtering DFR by Work Order Number and Purchase Order Number | Yet to Decide | Low | Customer Portal | 26.02.2023 | 16 |  | 16 | 8
10 | Have Production items segregated from Time and Material section | Yet to Decide | Medium | Customer Portal | 26.02.2023 | 4 |  | 4 | 2
11 | Mobile Application | Feb Release | High | Customer Portal | 26.02.2023 | 32 |  | 8 | 16
[6 empty] | 144 | 0 | 96 | 74
[6 empty] | 18 | 0 | 12 | 9.25