## CP - P3 - Status Tracking
Customer Portal - Phase III - Status Tracking
| User Story ID | User story Title | Apps | Dev Completion (%)
| CP-23 | DFR Signature | CP | 100
| CP-24 | Customer, Contract and Region Mapping | CP | 100
| CP-25 | Removing Labor and Equipment Comments | CP | 100
| CP-26 | Sign out Button UI | CP | 100
| CP-27 | User Role Mapping | CP | 75
| CP-28 | User Access screen for Mears Admin | CP | 60
| CP-29 | User Access screen for Client specific Admin | CP | 60
| CP-30 | Adding Password Reset Requirements | CP | 100
| CP-31 | Adding Requestor’s Name | CL | 90
| CP-32 | Requestor’s Name Validation | CP | 95
Completed
In Testing
In-Progress
Next work item
Not yet started

## Discussion Points
IT Changes/Discussion Point
S.No | Work Items | Responsible | Description
1 | CP SSRS: Need to display the image and Requestor name in SSRS report | Chris | How are we showing the image in CrewLink (what format)? - Need inputs from Vijay - png format
2 | CL Revenue/Billing export: Adding requestor name to column AH | Dhanesh
3 | CL App: Display ready to inspect button | Dhanesh | Introducing new column in CL WI_CONTRACT_MASTER_T and display the button based on this. 'Is_Customer_Portal' and 'Is_CP_Requester'
4 | CL Admin App: Customer Portal Contract Mapping | Kyle & Team | Update the CL WI_CONTRACT_MASTER_T new column through CL Admin app screen.
5 | CL: Display the 'Ready to Inspect' and 'Requester Name' based on flag instead of existing. | Dhanesh | Add a new column in CL WI_CONTRACT_MASTER_T table.
6 | CL: Conversion from Base64 to .png image | Vijay/Dhanesh | In CL this through C# code.
7 | CP: Removing the logic (SP) to pull the Labor/Equipment comments from CL | Vijay
Demo Feedback Points - Additional Changes
S.No | Items | Status
1 | Contact Us on Login & Forget Password Screen | Completed
2 | Transparent background for version number in header | Completed
3 | Add Help Button in header | Completed
4 | View Approval' button - Display the DFR Approval content in read only mode() | Completed
5 | Remove required text and keep only asterisk in approval screen | Completed
6 | Modify the stored proc bringing the labor and equipment comments | Completed
7 | Only view option in New Password | Completed
8 | Change the header to email instead of email Id in User Access | Completed
9 | Reset icon modification and displaying reset icon for all users | Completed
10 | Rename the Organization to Customer or Company ** - Finally it's Company | Completed
11 | Change mapping to Contract Mapping | Completed
12 | Title Change: 'Approval View' to 'Approval' in View Approval modal | Completed
13 | Pull the description for regions in Mapping Screen | Completed
14 | Profile Page | Next Release
15 | First name and last name fields separately editable | Next Release
16 | Adding time stamp in the signature stamp | Next Release

## Schema Changes
New changes
ContractRegionMapping_T(Customer Portal)
ID | bigint | Not Null
Contract | varchar(50) | Not Null
CompanyId | bigint | Null | Added a new column, foreign key - lookup
RegionID | bigint | Not Null
AddedBy | bigint | Not Null
AddedDate | datetime | Not Null
ChangedBy | bigint | Null
ChangedDate | datetime | Null
Active | bit | Not Null
TypeRoleScreenMapping_T (Customer Portal) |  |  | New Table
ID | bigint | Not Null
TypeRoleID | bigint | Not Null | Foreign key - Type Role Mapping
ScreenID | bigint | Not Null | Foreign key - Lookup
AddedBy | bigint | Not Null
AddedDate | datetime | Not Null
ChangedBy | bigint | Null
ChangedDate | datetime | Null
Active | bit | Not Null
DFRStatusTracking_T(Customer Portal)
ID | bigint | Not Null
JobMasterID | bigint | Not Null
StatusID | bigint | Not Null
Comment | varchar(MAX) | Null
AddedDate | datetime | Not Null
ChangedBy | bigint | Null
ChangedDate | datetime | Null
Active | bit | Not Null
CLUserId | bigint | Null
CPUserId | bigint | Null
ReasonTypeID | bigint | Null
CPIPAddress | nvarchar(25) | Null
CLUsername | varchar(50) | Null
CLUserRole | varchar(50) | Null
Signature | varbinary(MAX) | Null | Added a new column
Requester | nvarchar(25) | Null | Added a new column
CL_REQUESTER_NAME_TRACKING_T (Crewlink) |  |  | New Table
ID | bigint | Not Null
JOB_ID | bigint | Not Null
REQUESTER | varchar(80) | Null
CREATED_ON | datetime | Null
CREATED_BY | bigint | Null
ISACTIVE | bit | Not Null