## ActiveTaskList
S.No | Feature | Status | Priority | Application Concerned | Final Release Date | UI |  | API
1 | Extending Admin role to spire users | Feb Release | High | Customer Portal | 26.02.2023
2 | Reporting | Feb Release | High | Customer Portal | 26.02.2023 | 40 hours | Low | 24 hours
3 | Adding Copyright | Mid Feb Release | Medium | Customer Portal | 03.02.2023 |  | Medium | NIL
4 | "No Record Found" Feature | Mid Feb Release | Low | Customer Portal | 03.02.2023 | 4 hours | High | NIL
5 | Job Deletion Feature | Feb Release | Low | Crewlink & Customer Portal | 26.02.2023 | 4 hours |  | 16 hours
6 | Labor Comments section - Not appearing | Mid Feb Release | Low | Customer Portal | 03.02.2023 | 4 hours |  | 4 hours
7 | Mears Admin to be able to see the Approval and Reports screen in “View Only” mode to ease the bug fixing process if any | Yet to Decide | Low | Customer Portal | 26.02.2023 | 16 hours |  | 8 hours
8 | Having DFR Approval Status view in Reviewer screen | Yet to Decide | High | Crewlink | 26.02.2023 | 8 hours |  | 8 hours
9 | Filtering DFR by Work Order Number and Purchase Order Number | Yet to Decide | Low | Customer Portal | 26.02.2023
10 | Have Production items segregated from Time and Material section | Yet to Decide | Medium | Customer Portal | 26.02.2023 | 8 hours |  | 8 hours
11 | Mobile Application | Feb Release | High | Customer Portal | 26.02.2023 | 40 hours |  | 8 hours
[6 empty] | 124 hours |  | 76 hours
[6 empty] | 15.5 days |  | 9.5 days